## Project schedule
| CIVE 202 Project #3 | [5 empty] | Project start: | [7 empty] | 2026-02-27 | [11 empty] | Project end: | [7 empty] | 2026-03-31
|  | Project lead | Elizabeth Wiggins |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13
| TASK |  | PROGRESS | START | END | time axis 2026-02-23 to 2026-04-19
 | time axis 2026-02-23 to 2026-04-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Data cleaning and processing
| Import CSV Data to Python |  | 0% | 2026-02-27 | 2026-03-06 | 8
| Clean & Simplify CSV Data to Prepare for Graphing |  | 0% | 2026-03-06 | 2026-03-07 | 2
| Assign Variables to Cleaned Data |  | 0% | 2026-03-07 | 2026-03-08 | 2
Writing code
| Plot Bar Chart Comparing Categories |  | 0% | 2026-03-08 | 2026-03-15 | 8
| Plot Histogram Showing Distribution |  | 0% | 2026-03-08 | 2026-03-15 | 8
| Plot Boxplot Showing Distribution |  | 0% | 2026-03-08 | 2026-03-15 | 8
| Plot 2 Time-Series Plots Analyzing Driver Behavior |  | 0% | 2026-03-08 | 2026-03-15
| Simulation Study Using Intelligent Driver Model |  | 0% | 2026-03-08 | 2026-03-18 | 11
Writing documentation
| Scope of work |  | 0% | 2026-02-27 | 2026-03-06 | 8
| Annotated code document |  | 0% | 2026-03-09 | 2026-03-21 | 13
| Timesheet |  | 0% | 2026-02-27 | 2026-03-31
| Technical report |  | 0% | 2026-03-06 | 2026-03-30 | 25
Final project integration and submission
| Finalize & submit deliverables |  | 0% | 2026-03-30 | 2026-03-31 | 2
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]