## Gantt Chart
CIVE 202 – Project #4 Interpret: Gantt Chart
Mina Awad, Ava Johnson, Elizabeth Wiggins ¦ Submitted to: Dr. Kaycie Lane, P.E. ¦ University of California & Colorado–Omaha
Task | Assignee | Duration | 04/02 | 04/03 | 04/04 | 04/05 | 04/06 | 04/07 | 04/08 | 04/09 | 04/10 | 04/11 | 04/12 | 04/13 | 04/14 | 04/15 | 04/16 | 04/17 | 04/18 | 04/19 | 04/20 | 04/21
Task 1: Data Loading and Verification
1.1 Load NRI Census Tract & county data into pandas | Awad / Johnson | Apr 02 – Apr 03
1.2 Load SVI dataset (California.csv & Colorado.csv) | Wiggins | Apr 02 – Apr 03
1.3 Verify row counts, column counts & data types | Awad | Apr 03 – Apr 04
1.4 Review NRI Data Dictionary for variable definitions | Johnson / Wiggins | Apr 03 – Apr 04
Task 2: Data Cleaning & Dataset Integration
2.1 Handle -999 sentinel values in RPL_THEMES (68 CA + 16 CO tracts) | Awad | Apr 04 – Apr 06
2.2 Standardize FIPS codes for NRI / SVI merge | Johnson | Apr 04 – Apr 06
2.3 Merge NRI Census Tract data with SVI dataset | Awad / Johnson | Apr 06 – Apr 07
2.4 Verify merge completeness (9,106 CA + 1,447 CO tracts matched) | Wiggins | Apr 07 – Apr 08
Task 3: Alternative Risk Score Calculation
3.1 Implement alternative risk formula in Python | Awad | Apr 08 – Apr 10
3.2 Calculate ALT_RISK_SCORE for all 9,041 CA + 1,431 CO valid tracts | Awad | Apr 10 – Apr 11
3.3 Bin scores into qualitative rating categories | Johnson | Apr 11 – Apr 12
3.4 Sensitivity analysis — vary EAL / SVI weights | Awad / Johnson | Apr 12 – Apr 13
Task 4: Summary Tables and Figures
4.1 Cross-tabulation: NRI vs. alternative ratings | Johnson | Apr 13 – Apr 15
4.2 Distribution plots (NRI vs. alternative) | Wiggins | Apr 13 – Apr 15
4.3 Hazard-specific EAL figures (tornado, hail) | Johnson / Wiggins | Apr 14 – Apr 16
Task 5: GeoPandas Mapping
5.1 Download CA & CO Census Tract shapefiles | Wiggins | Apr 13 – Apr 14
5.2 Merge risk data with shapefile | Awad | Apr 14 – Apr 15
5.3 Generate choropleth map (NRI & alternative) | Awad / Wiggins | Apr 15 – Apr 17
Task 6: Documentation & Deliverables
6.1 Scope of Work | Awad | Apr 02 – Apr 04
6.2 Gantt chart | Awad | Apr 02 – Apr 04
6.3 Engineering timesheet | All | Apr 02 – Apr 20
6.4 Annotated code document | Johnson | Apr 16 – Apr 19
6.5 GitHub repository setup & README | Awad | Apr 18 – Apr 20
Task 7: Technical Report
7.1 Draft Methodology section | Awad / Johnson | Apr 14 – Apr 17
7.2 Draft Results & Discussion | Wiggins / Johnson | Apr 17 – Apr 19
7.3 Ethical implications & bias analysis | All | Apr 18 – Apr 20
7.4 References & final formatting | Awad | Apr 19 – Apr 20
Final Review & Submission | All | Apr 20 – Apr 21
Legend:
Data Loading & Verification
Data Cleaning & Integration
Alternative Risk Score
Summary Tables & Figures
GeoPandas Mapping
Documentation
Technical Report
Final Review & Submit
Task Dependencies:
Task 1 (Data Loading) → No dependencies; all other tasks depend on this
Task 2 (Data Cleaning & Integration) → Requires Task 1 completion; NRI and SVI must be loaded before merging
Task 3 (Alternative Risk Score) → Requires Task 2; merged NRI+SVI dataset must exist before computing scores
Task 4 (Summary Tables & Figures) → Requires Task 3; alternative risk ratings must be calculated before comparison
Task 5 (GeoPandas Mapping) → Requires Task 3; alternative scores must be merged into shapefile for choropleth maps. Partially overlaps Task 4
Task 6 (Documentation) → SOW and Gantt chart begin with Task 1; annotated code document requires Tasks 3–5 to be complete
Task 7 (Technical Report) → Requires Tasks 4 and 5; results, figures, and maps must be generated before writing the discussion and ethical analysis
Final Review → Requires all tasks complete