## Project schedule
| CIVE 202 Project #2 | [5 empty] | Project start: | [7 empty] | 2026-02-12 | [11 empty] | Project end: | [7 empty] | 2026-02-24
[7 empty] | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-02-09 to 2026-04-05
 | time axis 2026-02-09 to 2026-04-05
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Data cleaning and processing
| Translate Excel Logic to Python | Elizabeth Wiggins | 100% | 2026-02-12 | 2026-02-19 | 8
| Replicate Calculations | Oluwajuwon Omomeji-Sam | 100% | 2026-02-19 | 2026-02-20 | 2
| Define calculations as functions | Elizabeth Wiggins | 100% | 2026-02-20 | 2026-02-21 | 2 | 2026-02-21: ❶
Writing code
| User prompt functions | Elizabeth Wiggins | 100% | 2026-02-19 | 2026-02-21 | 3
| Calculations based on user input | Oluwajuwon Omomeji-Sam | 100% | 2026-02-20 | 2026-02-22 | 3
| Final mix design output | Elizabeth Wiggins | 100% | 2026-02-22 | 2026-02-23 | 2 | 2026-02-22: ❶
| Evaluate four concrete mix scenarios | All | 100% | 2026-02-23 | 2026-02-23 | 1 | 2026-02-23: ❷
Writing documentation
| Scope of work | Oluwajuwon Omomeji-Sam | 100% | 2026-02-12 | 2026-02-17 | 6
| Annotated code document | Elizabeth WIggins | 100% | 2026-02-20 | 2026-02-23 | 4
| Technical report | All | 100% | 2026-02-17 | 2026-02-23 | 7
Final project integration and submission
| Finalize & submit deliverables | All | 100% | 2026-02-23 | 2026-02-24 | 2
Insert new rows ABOVE this one